## Contents
#VALUE!
Additional Application Information - Skills Innovation Fund
This Additional Application Information spreadsheet should be completed and submitted with all applications.
You can upload this document and any other relevant supporting evidence within the online application form.
The purpose of this document is to provide clarity and ensure that applicants are in a position to create a basic project delivery plan.
Alongside the narrative explanation given in the application form, this completed document will enable appraisers to understand your project's deliverability, impact, and value for money.
Please read the Guidance on each tab before completing the tables.
Tabs to complete:
1) PROJECT PLAN
2) COST BREAKDOWN
3) RISK REGISTER
4) OUTPUTS & OUTCOMES

## 1) PROJECT PLAN
PROJECT PLAN - Guidance
In addition to the narrative information provided in the Application Form, please complete the table below to create a Project Plan.
Please only enter information into the yellow shaded areas.
You do not need to enter information into all available spaces.
Examples of Project Milestones might include (but are not limited to):
Securing the funding / Securing the necessary permissions / Appointing a project coordinator / Delivery of specified Events and Activities / Installation of Equipment / Survey and Evaluation work
For the Description, give a short outline of what activity is involved in this milestone.
Where possible, give Estimated Start Dates and Completion Dates for each milestone of the project
You may insert more rows to extend the table if more milestones need to be included.
Project Title:
| Project Milestone | Description | Estimated Start Date | Estimated Completion Date
1
2
3
4
5
6
7
8
9
10
…

## 2) COST BREAKDOWN
COST BREAKDOWN - Guidance
Please complete the tables below to provide more detailed Financial Information
Please only enter information into the yellow shaded areas.
You do not need to enter information into all available spaces.
The project budget should be secured with costs known and quantified. This will allow the YNYCA to appraise the application and determine the project's value for money.
The project deliverer must guarantee to cover any cost inflation or overruns that occur during the project. The YNYCA cannot make allowances for unexpected increases in project costs.
Complete the first table below with all Items of Expenditure involved in delivering the project.
For each item, provide its cost to the best of your knowledge and indicate whether it is Revenue or Capital expenditure.
Where possible, include a date by which you expect this expenditure will have taken place.
All individual items of expenditure will be added together to give a Total Project Expenditure sum.
This sum will populate the Total Cost of your project in the second table below.
Please insert how much funding you are applying for.
Match funding is not mandatory for this programme (meaning an Intervention Rate of 100% is acceptable).
However, the inclusion of match funding (lowering the intervention rate down from 100%) will be considered favourably in the appraisal process.
You may insert more rows to extend the table if more Items need to be included.
| Item of Expenditure | Cost (£) | Revenue or Capital Expenditure | Expected Date of Expenditure
1 |  | 0
2 |  | 0
3 |  | 0
4 |  | 0
5 |  | 0
6 |  | 0
7 |  | 0
8 |  | 0
9 |  | 0
10 |  | 0
11 |  | 0
12 |  | 0
13 |  | 0
14 |  | 0
15 |  | 0
16 |  | 0
17 |  | 0
18 |  | 0
19 |  | 0
20 |  | 0
... |  | 0
| Total Project Expenditure | 0
Total Project Expenditure
| Question | £ | Intervention Rate Calculator
| What is the Total Cost of your project? | 0
| How much funding are you applying for from the YNYCA? | 0 | Intervention Rate Proportion of the project funded by the YNYCA (%) | n
| How much match funding are you planning to secure? | 0 | Proportion of the project match funded (%) | n

## 3) RISK REGISTER
RISK REGISTER - Guidance
In addition to the narrative information provided in the Application Form, please complete the table below to create a Risk Register
Please only enter information into the yellow shaded areas.
You do not need to enter information into all available spaces.
The Risk Description should be a short outline of a key risk you have identified. This could be a Delivery Risk, Financial Risk, Reputational Risk, Environmental Risk, etc.
Provide an initial Assessment of Risk (Low / Medium / High using the Drop-Down). You may take into account the potential adverse impact and the likelihood of this occurring.
Explained what your Planned Mitigation is to reduce or limit this identified risk.
Provide a Revised Assessment of Risk (Low / Medium / High using the Drop-Down) based on the Planned Mitigation action you will take.
You may insert more rows to extend the table if more risks need to be included.
| Risk Description | Assessment of Risk | Planned Mitigation | Revised Assessment of Risk
1
2
3
4
5
6
7
8
9
10
…

## 4) OUTPUTS & OUTCOMES
OUTPUTS & OUTCOMES - Guidance
In addition to the narrative information provided in the Application Form, please complete the table below to clarify the project Outputs and Outcomes.
Please only enter information into the yellow shaded areas.
You do not need to enter information into all available spaces. Please focus on those Outputs and Outcomes your project can realistically deliver.
For the Selected Output and Selected Outcome column, choose from the Drop-Down list of options available.
Any 'Other' relevant Outputs/Outcomes specified in your application can be included here too. If 'Other' is selected, please specify this in the 'Baseline Level' cell.
For the Baseline Level, give or describe the current level of this Output/Outcome you are experiencing. What would the number continue to be if the project did not go ahead?
For the Target Quantity, please specify how many you are aiming to deliver over the course of the project.
Please provide realistic targets for your project. If your application is successful, the figures given here will inform a key part of the Grant Funding Agreement.
For the Expected Delivery Date please indicate when you expect these Outputs and Outcomes will be delivered.
You may insert more rows to extend the Table if more Outputs and Outcomes need to be included.
| Selected Output/Outcome | Baseline Level | Target Quantity | Expected Delivery Date
1
2
3
4
5
6
…

## Inputs (hidden)
COST BREAKDOWN | RISK REGISTER |  | OUTPUTS & OUTCOMES
Revenue | Low | Low | Improved teaching facilities
Capital | Medium | Medium | New flexible courses (bite sized, modular, outreach) developed and delivered
| High | High | Increased number of tutors trained in industry related skills
Increased number of adult learners trained in priority sectors, focusing on disengaged learners and those in need of upskilling and reskilling
Improved recruitment rate of teaching staff
Improved retention rate of teaching staff
Other 1
Other 2
Other 3